# Project Review and Monitoring Report

Car Rental Booking System (FAST CARS) · Prepared by Abubakr Abdulkareem (Person 3) · Draft, 21 Oct 2026

## 1. Project details

| Item | Details |
| --- | --- |
| Project title | Car Rental Booking System |
| Client | FAST CARS |
| Technology | Python, Django, SQLite |
| Repository | https://github.com/Timi-08/CarRentals |
| Team size | 4 |

### Team and responsibilities

| Person | Team member | Area |
| --- | --- | --- |
| 1 | Timilehin | Accounts, administrator dashboard, project integration, Problem Definition, CRS, Project Plan, Task Sheet |
| 2 | Isreal | Vehicle catalogue, contact and site content, E-R Diagrams, Algorithms |
| 3 | Abubakr Abdulkareem | Booking system, testimonials, testing, Unit Testing Check List, this report, Final Check List |
| 4 | Daniel | Shared frontend, GUI Standards, Interface Design, Certificate of Completion, Table of Contents |

## 2. Progress against the Project Plan

Planned dates come from the Project Plan and Task Sheet prepared by Timilehin. Actual dates come from the GitHub history.

| Milestone | Owner | Planned date | Actual date | Status | Remarks |
| --- | --- | --- | --- | --- | --- |
| Problem Definition and CRS | Timilehin |  | 8 Oct 2026 | Done | Shared with the team |
| Accounts module | Timilehin |  | 16 Oct 2026 | Done | Merged into main |
| Booking and testimonials modules | Abubakr |  | 19 Oct 2026 | Done | Pull request #1 open; Vehicle integration pending |
| Vehicle catalogue and contact modules | Isreal |  |  | In progress | Not yet merged into main |
| Shared frontend | Daniel |  | 21 Oct 2026 | In review | Branch pushed, not yet merged |
| Integration and final testing | Team |  |  | Not started | Needs every module in main |

## 3. Review of my modules (Person 3)

| Requirement | Summary | Result |
| --- | --- | --- |
| BKG-01 to BKG-12 | Booking creation, validation of dates, availability and overlaps, price calculation, Pending to Confirmed or Cancelled workflow, customer history, admin management | Implemented, covered by automated tests |
| TST-01 to TST-03 | Customers post testimonials, only active ones are public, admin activates or deactivates | Implemented, covered by automated tests |
| NFR-04 | Paginated lists: my bookings, manage bookings, testimonials | Implemented, tested |
| NFR-06 | Database rule rejecting a return date on or before the pickup date; overlaps blocked by validation | Implemented, tested |

Decisions on the open point in the CRS: Pending and Confirmed bookings block overlapping dates, Cancelled bookings do not, and a booking may start on the day another one for the same vehicle ends. A customer may cancel only while a booking is Pending.

## 4. Testing summary

The booking and testimonial modules have automated tests run with python manage.py test. Every requirement ID has a test case in the Unit Testing Check List, where results are recorded as each module is merged and checked.

## 5. Issues and resolutions

| # | Issue | Resolution |
| --- | --- | --- |
| 1 | The accounts migration was missing, so creating the first user failed because the profile table did not exist | Timilehin committed the accounts migration (merged into main on 16 Oct) |
| 2 | The database file and compiled Python files were tracked in Git, risking merge conflicts | A .gitignore was added and the database file was removed from tracking |
| 3 | Booking depends on the Vehicle model owned by another module | Booking was built against a temporary stand-in; field names were later confirmed against the real model |
| 4 | The real Vehicle model requires a seat count, which the first tests did not set | Tests were updated to create a brand and seats |
| 5 | The CRS left open which statuses block an overlap and when customers may cancel | Decision recorded in section 3 |
| 6 | The first push to the shared repository was refused for lack of access | Access was granted by the repository owner |
| 7 | The navbar link for administrators to manage bookings points to the customer page | Reported to the frontend owner |
| 8 | The vehicle detail page has no link to the booking form | Reported to the vehicle module owner |

## 6. Open risks

| Risk | Mitigation |
| --- | --- |
| Booking code cannot start without the Vehicle model, so merge order matters | Merge the vehicle module first, then the booking pull request |
| SQLite cannot enforce non-overlapping date ranges at database level | Overlaps are blocked by validation in the model; documented as a known limit |
| Documents depend on other members finishing theirs | Weekly check-in and Task Sheet follow-up |

## 7. Team coordination

### Weekly check-ins

| Date | Attendees | Summary | Actions |
| --- | --- | --- | --- |

### Status reports

| Report | Due date | Sent date | Remarks |
| --- | --- | --- | --- |
| 1st status report |  |  |  |
| 2nd and final status report |  |  |  |

## 8. Overall assessment

The booking and testimonial modules are feature-complete against the CRS. Remaining work for this part is integration with the merged Vehicle model, restyling with the shared frontend, and re-running the full test suite once every module is in main.